## INTERFACES & REPORTING
Priority | Business Area | System Impacted | IT Business Resource | IT Integration Resource | Integration Status | Interface, Conversion, or Reporting Requirement | Application | From Platform | From Application | To Platform | To Application | Division | Interface Description | Current Method | FINANCE Phase | SALES & TRANS Phase | MFG. Phase | Interface/Conversion | M3 API | Input | Output | Frequency | Mapping | Table | Notes
1 | General Ledger | JDE | BARB |  |  | I | GL | AS400 | JDE | SQL | M3 | ALL | Initial Account Balances for M3 - Ongoing on a Monthly Basis for Consolidation in M3 | *NONE | Temporary |  |  | edi? Invoice Scanner?; Manual; Seaboard Foods Carrier Payment - EDI, Invoice Scanner? Manual?
1 | Procure to Pay | Bank | BARB |  |  | I | AP | FTP? | Bank Of America | SQL | M3 | TF | AP Bank Reconciliation (Cleared Checks) | Automated | Permanent
1 | Procure to Pay | Bank | BARB |  |  | I | AP | FTP? | Bank Of New York | SQL | M3 | SBD | AP Bank Reconciliation (Cleared Checks) | Automated | Permanent
1 | Procure to Pay | Bank | BARB |  |  | I | AP | SQL | M3 | ? | Bank of America | TF | Possitive Pay | Automated | Permanent
1 | Procure to Pay | Bank | BARB |  |  | I | AP | SQL | M3 | ? | Bank of America | TF | Automatic Clearing House (ACH) | Automated | Permanent
1 | Procure to Pay | Bank | BARB |  |  | I | AP | SQL | M3 | ? | Bank of New York | SBD | Possitive Pay | Automated | Permanent
1 | Procure to Pay | Bank | BARB |  |  | I | AP | SQL | M3 | ? | Bank of New York | SBD | Automatic Clearing House (ACH) | Automated | Permanent
1 | Procure to Pay | Bank | BARB |  |  | I | AP | SQL | M3 | ? | Sun Trust Bank | ? | Credit Card Payment | Automated | Permanent
1 | Procure to Pay | CAT2 | PAUL |  |  | I | PO | SQL | CAT2 | SQL | M3 | DPM | Purchase Order Receipts Units/Lot Numbers | *NONE | Permanent
1 | Procure to Pay | CAT2 | PAUL |  |  | I | PO | SQL | CAT2 | SQL | M3 | DPM | Update Inventory (Issue Transactions) | *NONE | Permanent |  |  | Talked to Jennifer Smith regarding new Item Codes for Packaging Items on 11/04/2014. She indicated that a decision was made to use existing Packaging Item Codes as they are in MP2 and other systems. It was decided during this meeting with Jennifer that she would work with Damon Ginther on the Business Processes regarding management of Packaging Items needed on the AS400 for Packaging Variance Reports and the calculation of Miscellaneous Tare Weights for Finished Goods Items.
1 | Procure to Pay | CAT2 | BARB |  |  | I | PO | SQL | M3 | SQL | CAT2 | DPM | Purchase Orders Header/Detail | Automated | Temporary | Temporary | M3
1 | Procure to Pay | CAT2 | BARB |  |  | I | PO | SQL | M3 | SQL | CAT2 | DPM | Purchase Order Receipts Units/Lot Numbers | *NONE | Temporary | Temporary | M3 | HPE to AP Manual Payment AP20? GL01? Will this handle both AP and GL? | Yes | x | x | daily or monthly
1 | Procure to Pay | JDE | BARB |  |  | C | GL | AS400 | JDE | SQL | M3 | ALL | Initial Account Balances for M3 | *NONE | Temporary |  |  | HPE to AP Manual Payment AP20? GL01? Will this handle both AP and GL?
1 | Procure to Pay | OMS | ? |  |  | I | PO | SQL | M3 | AS400 | OMS | SBD | Procurement - Packaging Items | Manual | Manual
1 | Procure to Pay | OMS | ROSE |  |  | I | PO | SQL | M3 | AS400 | OMS | SBD | Packaging Usage | Automated | Temporary | M3 |  | Seaboard Transport
2 | Procure to Pay | HPE | SUSAN BARB |  |  | I | AP/GL | AS400 | HPE | SQL | M3 | SBD; TF | Producer Payment | Automated | Permanent |  |  | Seaboard Transport
2 | Procure to Pay | HPE | SUSAN BARB |  |  | I | AP/GL | AS400 | HPE | SQL | M3 | SBD; TF | Trucker Payment | Automated | Permanent |  |  | POWER PRO to AR Invoice AR10 | Yes | x | x | daily, could be multiple times |  |  | #3 priority
2 | Procure to Pay | HPE | ROSE |  |  | I | MASTER | SQL | M3 | AS400 | HPE | SBD; TF | Supplier/Vendor Master (Producer's Only) | *NONE | Permanent |  |  | POWER PRO TO AR Payments AR30 | Yes | x | x | daily, could be multiple times
3 | Procure to Pay | Power Pro | BARB |  |  | I | AP/GL | SQL | POWER PRO | SQL | M3 | STI | Carrier/Trucker Payment | Automated | Permanent
3 | Procure to Pay | Power Pro | BARB |  |  | I | AP/GL | SQL | POWER PRO | SQL | M3 | STI | Driver Payment | Automated | Permanent |  |  | AGRIS to AP Manual Payment AP20?GL01? | Yes | x | x | daily or monthly
3 | Procure to Pay | Power Pro | BARB |  |  | I | GL | SQL | POWER PRO | SQL | M3 | STI | Freight Billing | Automated | Permanent
3 | Procure to Pay | Power Pro | BARB |  |  | I | GL | SQL | POWER PRO | SQL | M3 | STI | Cash Receipts | Automated | Permanent |  |  | AGRIS to AP Manual Payment AP20?GL01? | Yes | x | x | daily or monthly
4 | Procure to Pay | Agris | DAVID W. |  |  | I | GL | ACCESS? | AGRIS | SQL | M3 | SBD | Grain Supplier Payment | Manual | Permanent |  |  | Will this be the same format as all other GL Entries?
4 | Procure to Pay | Agris | DAVID W. |  |  | I | AP | ACCESS? | AGRIS | SQL | M3 | SBD | Grain Supplier Payment | Manual | Permanent
7 | Inventory | CARLISLE | ROSE |  |  | I | Shop Floow | SQL | CARLISLE | SQL | M3 | TF | Production | *NONE |  | Permanent |  | TFS to GL Claims Adjustment | Yes | x | x | multiple times daily
7 | Order to Cash | Bank | BARB |  |  | I | AR | FTP | Bank Of New York | SQL | M3 | SBD | Accounts Receivable Lockbox | Automated | Permanent |  |  | TFS to GL for Cash Distribution | Yes | x | x | multiple times daily
7 | Order to Cash | OMS | ROSE |  |  | C | AR/GL | AS400 | OMS | SQL | M3 | SBD; TF; DPM; HPB | Open AR Customer Invoice/Credit & Debit Memo |  |  |  |  | TFS to GL AR# adjustment | Yes | x | x | multiple times daily
7 | Order to Cash | TFS REWRITE | LEANNE |  |  | I | GL | AS400 | TFS | SQL | M3 | SBD;TF | Revenue Adjustment | Automated | Temporary |  |  | HPS to GL& Budget? Units
7 | Order to Cash | TFS REWRITE | LEANNE |  |  | I | GL | AS400 | TFS | SQL | M3 | SBD;TF | Cash Distribution | Automated | Temporary
7 | Order to Cash | TFS REWRITE | LEANNE |  |  | I | GL | AS400 | TFS | SQL | M3 | SBD;TF | Claim Adjustment | Automated | Temporary
7 | Order to Cash | TFS REWRITE | LEANNE |  |  | I | GL | AS400 | TFS | SQL | M3 | SBD;TF | AR Adjustment | Automated | Temporary
7 | Order to Cash | OMS | BARB ROSE |  |  | C | AP | AS400 | OMS or JDE | SQL | M3 | SBD; DPM; TF; HPB | Initial Customer Master | *NONE | Temporary/One Time |  |  | TFS to GL for Revenue Adjustments | Yes | x | x | multiple times daily
9 | Inventory | JDE | DUSTIN |  |  | C | GL | SQL | M3 | SQL | MTECH | SBD | Account Balances | Automated | Temporary |  |  | Replaced by M3
9 | Inventory | MTECH | DUSTIN |  |  | I | GL | SQL | MTECH | SQL | M3 | SBD | Cull Sales Dollars | Automated | Permanent |  |  | Replaced by M3
9 | Inventory | MTECH | DUSTIN |  |  | I | GL | SQL | MTECH | SQL | M3 | SBD | Feed Delivery Dollars | Automated | Permanent |  |  | Replaced by M3
9 | Inventory | MTECH | DUSTIN |  |  | I | GL | SQL | MTECH | SQL | M3 | SBD | Feed Delivery Pounds | Automated | Permanent
9 | Inventory | MTECH | DUSTIN |  |  | I | GL | SQL | MTECH | SQL | M3 | SBD | Feed Pick Up Dollars | Automated | Permanent
9 | Inventory | MTECH | DUSTIN |  |  | I | GL | SQL | MTECH | SQL | M3 | SBD | Pig Days | Automated | Permanent
9 | Inventory | MTECH | DUSTIN |  |  | I | GL | SQL | MTECH | SQL | M3 | SBD | Semen Doses Delivered | Automated | Permanent |  |  | Triumph Fees and Payment - AR/CD Recon
9 | Inventory | MTECH | DUSTIN |  |  | I | GL | SQL | MTECH | SQL | M3 | SBD | Semen Doses Shipped | Automated | Permanent |  |  | Triumph Fees and Payment - AR/CD Recon
9 | Inventory | MTECH | DUSTIN |  |  | I | GL | SQL | MTECH | SQL | M3 | SBD | Transfer Out Different Phase | Automated | Permanent |  |  | Triumph Fees and Payment - AR/CD Recon
9 | Inventory | MTECH | DUSTIN |  |  | I | GL | SQL | MTECH | SQL | M3 | SBD | Units | Automated | Permanent |  |  | OMS to AR10 OMS invoices | Yes | x | x | daily, could be multiple times |  |  | #2 priority
10 |  |  | BARB |  |  | R | Tax | SQL | M3 | LOCAL | XLS | ALL | Account Balances | Automated | Permanent |  |  | Will this be the same format as all other GL Entries?
99999 | OBSOLETE | DPM Purchasing |  |  | Not Needed | I | AP | AS400 | DPM Legacy (Tom E) | SQL | M3 | DPM | Supplier Payment | Manual | M3 |  |  | OMS to OCUSMA (Total Value Orders Not Shipped) | Yes | x | x | daily, could be multiple times
99999 | OBSOLETE | MP2 |  |  | Not Needed | I | AP | SQL | MP2 | SQL | M3 | SBD | Supplier Payment | Automated | M3
99999 | OBSOLETE | MP2 |  |  | Not Needed | I | AP | SQL | MP2 | SQL | M3 | TF | Supplier Payment | Manual | M3
Not Needed | Order to Cash | OMS | ? AARON L. |  |  | I | AR/GL | AS400 | OMS | SQL | M3 | SBD; TF; DPM; HPB | OCUSMA (Total Values Orders Not Shipped) | ? | ? | ? |  | HPS to GL Sales dollars | Yes | x | x | monthly
Not Needed | Order to Cash | OMS | ROSE |  |  | I | AR | SQL | M3 | AS400 | ARS | SBD; TF | AR Header | *NONE | Temporary | NEW APP
Not Needed | Order to Cash | OMS | ROSE |  |  | I | MASTER | SQL | M3 | AS400 | OMS | SBD; TF; DPM; HPB | Customer Master | *NONE | Temporary | M3 |  |  | Yes | x | x | monthly
Not Needed | Order to Cash | OMS | ROSE |  |  | I | AR | SQL | M3 | AS400 | ARS | SBD; TF | AR Detail | *NONE | Temporary | NEW APP |  | HPS to GL & Budget? Feed Delivery # & $ | Yes | x | x | monthly
Not Needed | Order to Cash | OMS | ROSE |  |  | I | AR | SQL | M3 | AS400 | ARS | SBD; TF | AR On Account Detail | *NONE | Temporary | NEW APP |  | HPS Feed Pickup dollars | Yes | x | x | monthly
Not Needed | Order to Cash | OMS | ROSE |  |  | I | AR/GL | AS400 | OMS | SQL | M3 | SBD; TF; DPM; HPB | Customer Invoice/Credit & Debit Memo | Automated | Temporary | M3 |  | HPS to GL& Budget? Semen doses | Yes | x | x | monthly
Not Needed | Order to Cash | OMS |  |  |  | I | GL | AS400 | OMS | SQL | M3 | SBD; TF; DPM; HPB | Monthly Revenue Adjustment (Domestic/Export) | Manual | ? |  |  |  | Yes | x | x | monthly
Not Needed | Order to Cash | OMS |  |  |  | I | GL | AS400 | OMS | SQL | M3 | SBD; TF; DPM; HPB | Inventory Stock Closing/Value | Manual | ? |  |  | HPS to GL& Budget? Transfer Out Diff phase
Not Needed | Order to Cash | OMS |  |  |  | I | AP | AS400 | OMS | SQL | M3 | SBD; TF; DPM; HPB | Carrier Payment | Manual | Manual | Permanent (EDI?) |  | HPS Pigs Days to GL & Budget? | Yes | x | x | monthly
Not Needed | Procure to Pay | Utility | JOHN L. |  |  | I | AP/GL | SQL | UIAA (all ATT bill) | SQL | M3 | SBD | Phone Bill Payment | Automated (John Lalumondier) | Permanent
Stay in JDE |  | ADP | BARB |  |  | I | GL | ? | ADP | SQL | M3 | SBD | Pay Gross | Automated | Permanent

## Frank's Sheet
Business Area | Application | Interface Description | load frequency | complexity | duration | resources | Phase | Tech for load | comments |  | duration buckets complexity 1 - 4 = 2 weeks complexity 5 - 7 = 4 weeks complexity 8-10 = 4 + weeks note there are multiple banks for ACH, positive pay, and reconcilliation
Inventory | GL | Account Balances | MTECH | 0 |  | Dustin
Inventory | GL | Cull Sales Dollars | MTECH | 0 |  | Dustin
Inventory | GL | Feed Delivery Dollars | MTECH | 0 |  | Dustin
Inventory | GL | Feed Delivery Pounds | MTECH | 0 |  | Dustin
Inventory | GL | Feed Pick Up Dollars | MTECH | 0 |  | Dustin
Inventory | GL | Pig Days | MTECH | 0 |  | Dustin
Inventory | GL | Semen Doses Delivered | MTECH | 0 |  | Dustin
Inventory | GL | Semen Doses Shipped | MTECH | 0 |  | Dustin
Inventory | GL | Transfer Out Different Phase | MTECH | 0 |  | Dustin
Inventory | GL | Units | MTECH | 0 |  | Dustin
| Tax | Account Balances |  | 0 |  |  |  |  | tax for corp accounting | will they have access to M3 to do their own extract? Probably not needed
Order to Cash | AR/GL | OCUSMA (Total Values Orders Not Shipped) | ? | 0 |  |  |  |  | need further discussion
Order to Cash | AR | AR Header | ? | 0 |  |  |  |  | need further discussion
Order to Cash | MASTER | Customer Master | ? | 0 |  |  |  |  | need further discussion
Order to Cash | AR | AR Detail | ? | 0 |  |  |  |  | need further discussion
Order to Cash | AR | AR On Account Detail | ? | 0 |  |  |  |  | need further discussion
Order to Cash | AR/GL | Customer Invoice/Credit & Debit Memo | ? | 0 |  |  |  |  | need further discussion
Order to Cash | GL | Monthly Revenue Adjustment (Domestic/Export) | ? | 0 |  |  |  |  | need further discussion
Order to Cash | GL | Inventory Stock Closing/Value | ? | 0 |  |  |  |  | need further discussion
Order to Cash | AP | Carrier Payment | ? | 0 |  |  |  |  | need further discussion
General Ledger | GL | Account Balances for M3 - Ongoing on a Monthly Basis for Consolidation in M3 | monthly | 2 | 2 | B, R, F, Aram | 1 | ION/MEC
General Ledger | GL | Account Balances for M3 - Ongoing on a Weekly Basis for Consolidation in M3 | weekly | 2 | 2 | B, R, F, Aram | 1 | ION/MEC
General Ledger | GL | Account Balances for M3 - Ongoing on a Daily Basis for Consolidation in M3 - TBD | daily | 2 | 2 | B, R, F, Aram | 1 | ION/MEC
Procure to Pay | PO | Packaging Usage | weekly | 4 | 2 | B, R, F | 1 | ION/MEC | usage coming from M3
Procure to Pay | MASTER | Supplier/Vendor Master | inter-day/event based | 4 | 2 | B,R,F | 1 | ION/MEC | part of master data synch
Procure to Pay | AP/GL | Carrier/Trucker Payment | inter-day | 5 | 4 | B,R,F, Veo Sananikone, Aram | 1 | ION/MEC | source is powerpor | Aram needs to validate codes in PowerPro to Dim mapping
Procure to Pay | AP/GL | Driver Payment | inter-day | 5 | 4 | B,R,F, Veo Sananikone, Aram | 1 | ION/MEC | source is powerpor | Aram needs to validate codes in PowerPro to Dim mapping
Procure to Pay | GL | Freight Billing | inter-day | 5 | 4 | B,R,F, Veo Sananikone, Aram | 1 | ION/MEC | source is powerpor | Aram needs to validate codes in PowerPro to Dim mapping. Need to validate if transactions are needed vs. just balances
Procure to Pay | GL | Cash Receipts | inter-day | 5 | 4 | B,R,F, Veo Sananikone, Aram | 1 | ION/MEC | source is powerpro | Aram needs to validate codes in PowerPro to Dim mapping. Need to validate if transactions are needed vs. just balances
Order to Cash | AP | Initial Customer Master | one time | 5 | 4 | B,R,F, Jennifer S. | 1&2 | ION/MEC | Dailys in phase 1, Foods in phase 2
Order to Cash | AP | Customer Master integration | inter-day | 5 | 4 | B,R,F,Jennifer S. | 1&2 | ION/MEC | Dailys in phase 1, Foods in phase 3
Procure to Pay | AP/GL | Phone Bill Payment (UIAA) | End of Month | 5 | 4 | B,R,F | 1 | ION/MEC | Process needs to be reviewed | need to get bills into M3
Procure to Pay | AP | AP Bank Reconciliation (Cleared Checks) | daily | 6 | 4 | B, R, F, Aram | 1 | EDI/Informatica | no api or mec process to do this
General Ledger | GL | Initial Account Balances for M3 - 2014 balances for consolidation in M3 | one time | 7 | 4 | B, R, F, Aram | 1 | M3 API | for trial balances in m3 | need to seed for EOY 2014 and EOM Jan 2015 -
Procure to Pay | AP | Positive Pay | daily | 7 | 4 | B, R, F, Aram | 1 | EDI/Informatica | no api or mec process to do this
Procure to Pay | AP/GL | Producer Payment | inter-day | 7 | 4 | B, R, F | 1 | ION/MEC
Procure to Pay | AP/GL | Trucker Payment | inter-day | 7 | 4 |  | 1 | ION/MEC
Order to Cash | AR | Accounts Receivable Lockbox | inter-day scheduled | 7 | 4 | B,R,F, Tim W. Nolan Shaw | 1 | ION/MEC | Bank input
Order to Cash | AR/GL | Open AR Customer Invoice/Credit & Debit Memo | inter-day/nightly | 7 | 4 | B,R,F, Tim W. Nolan Shaw |  | ION/MEC | do not need
| GL | ADP | weekly | 7 | 4 | B,R,F, Angie Childs |  | ION/MEC | confirm with Aram on what needs to be done here
| AP | 1099 | EOY | 7 | 4 |  |  | ION/MEC | will need to combine corp and foods for submission. Confirm with Aram can a vendor get one or multiple 1099's
Inventory | Shop Floor | Production | real time | 8 | 5 | B,R,F, Bruce, Steve | 1 | ION/MEC | CAT2 | this will replace the recstoration process
Order to Cash | GL | Revenue Adjustment | weekly | 10 | 5 | Mike B. | 2 | ION/MEC | Triumph Fees and Payments | this has to be discussed
Order to Cash | GL | Cash Distribution | weekly | 11 | 5 | Mike B. | 2 | ION/MEC | Triumph Fees and Payments | this has to be discussed
Order to Cash | GL | Claim Adjustment | weekly | 12 | 5 | Mike B. | 2 | ION/MEC | Triumph Fees and Payments | this has to be discussed
Order to Cash | GL | AR Adjustment | weekly | 13 | 5 | Mike B. | 2 | ION/MEC | Triumph Fees and Payments | this has to be discussed
Procure to Pay | AP | Automatic Clearing House (ACH) |  |  |  |  | 1 | UNKNOWN | streamserve will need to still generate notification of ACH
Procure to Pay | AP | Credit Card Payment |  |  |  |  | 1 |  | need to confirm with Jodie Ware if still needed.
Procure to Pay | PO | Purchase Order Receipts Units/Lot Numbers |  |  |  |  | 1 |  | cat
Procure to Pay | PO | Update Inventory (Issue Transactions) |  |  |  |  | 1 |  | cat
Procure to Pay | PO | Purchase Orders Header/Detail |  |  |  |  | 1 |  | cat
Procure to Pay | PO | Procurement - Packaging Items | [6 empty] | should be handled with item master integration (Foods) | need to discuss further
Procure to Pay | GL | Grain Supplier Payment | manual | [5 empty] | agris | Manual J/E to cover all checks for HPB and one J/E to cover all Seaboard Grain
|  |  |  | 165 | 6600