## Foods Finance Interfaces
Interface Description | Source | load frequency | complexity | duration (weeks) | resources | Phase | Tech for load | comments
Account Balances | MTECH | unknown | unknown |  | Dustin | 2
Cull Sales Dollars | MTECH | unknown | unknown |  | Dustin | 2
Feed Delivery Dollars | MTECH | unknown | unknown |  | Dustin | 2
Feed Delivery Pounds | MTECH | unknown | unknown |  | Dustin | 2
Feed Pick Up Dollars | MTECH | unknown | unknown |  | Dustin | 2
Pig Days | MTECH | unknown | unknown |  | Dustin | 2
Semen Doses Delivered | MTECH | unknown | unknown |  | Dustin | 2
Semen Doses Shipped | MTECH | unknown | unknown |  | Dustin | 2
Transfer Out Different Phase | MTECH | unknown | unknown |  | Dustin | 2
Units | MTECH | unknown | unknown |  | Dustin | 2
Initial Account balances for M3 | JDE | One time | 7 | 5 | B, R, F | 1
Account Balances for M3 - Ongoing on a Monthly Basis | JDE | Monthly | 2 | 2 | B, R, F | 1
Account Balances for M3 - Ongoing on a Weekly Basis | JDE | Weekly | 2 | 2 | B, R, F | 1
Account Balances for M3 - Ongoing on a Daily Basis | JDE | Daily | 2 | 2 | B, R, F | 1
Carrier/Trucker Payment | PowerPro | inter-day | 5 | 4 | B,R,F, Veo Sananikone, Aram | 1 | ION/MEC | Aram needs to validate codes in PowerPro to Dim mapping
Driver Payment | PowerPro | inter-day | 5 | 4 | B,R,F, Veo Sananikone, Aram | 1 | ION/MEC | Aram needs to validate codes in PowerPro to Dim mapping
Freight Billing | PowerPro | inter-day | 5 | 4 | B,R,F, Veo Sananikone, Aram | 1 | ION/MEC | Aram needs to validate codes in PowerPro to Dim mapping. Need to validate if transactions are needed vs. just balances
Cash Receipts | PowerPro | inter-day | 5 | 4 | B,R,F, Veo Sananikone, Aram | 1 | ION/MEC | Aram needs to validate codes in PowerPro to Dim mapping. Need to validate if transactions are needed vs. just balances
Phone Bill Payment (UIAA) | Manual | End of Month | 5 | 4 | B,R,F | 1 | ION/MEC | Process needs to be reviewed, need to get bills into M3
AP Bank Reconciliation (Cleared Checks) | Bank download | daily | 6 | 4 | B, R, F, Aram | 1 | EDI/Informatica | no api or mec process to do this
Positive Pay |  | daily | 7 | 4 | B, R, F, Aram | 1 | EDI/Informatica | no api or mec process to do this
Producer Payment |  | inter-day | 7 | 4 | B, R, F | 1 | ION/MEC
Trucker Payment |  | inter-day | 7 | 4 |  | 1 | ION/MEC
Accounts Receivable Lockbox |  | inter-day scheduled | 7 | 4 | B,R,F, Tim W. Nolan Shaw | 1 | ION/MEC | Bank input
ADP |  | weekly | 7 | 4 | B,R,F, Angie Childs |  | ION/MEC | confirm with Aram on what needs to be done here
1099 |  | EOY | 7 | 4 |  |  | ION/MEC | will need to combine corp and foods for submission. Confirm with Aram can a vendor get one or multiple 1099's
Production | CAT2 | real time | 8 | 5 | B,R,F, Bruce, Steve | 1 | ION/MEC | this will replace the recstoration process
Automatic Clearing House (ACH) | M3 | batch | 7 | 5 | B,R,F | 1 | UNKNOWN | streamserve will need to still generate notification of ACH to suppliers
Credit Card Payment | ? | ? | ? | ? | ? | 1 |  | need to confirm with Jodie Ware if still needed.
Grain Supplier Payment | Agris | manual | [5 empty] | Manual J/E to cover all checks for HPB and one J/E to cover all Seaboard Grain
Fixed Assets | M3 | ? | ? |  | B,R,F,Aram,David O. | 1 | unknown | fixed assets live before EOY, data to be synched back to JDE
Fixed Assets - Data conversion | GBA | one-time |  |  | Aram,David O., Bruce | 1

## Foods Procurement Interfaces
Interface Description | Source | load frequency | complexity | duration | resources | Phase | Tech for load | comments
Packaging Usage | M3 | weekly | 4 | 2 | B, R, F | Post Phase 1 | ION/MEC | usage coming from M3
receiving?

## Master Data Interfaces
Interface Description | Source | load frequency | complexity | duration (weeks) | resources | Phase | Tech for load | comments
Item Master | AS400/MP2 | event | 5 | 6 |  |  |  | complexity is based on how much data originates out of M3 vs. AS400
Customer Master | AS400 | event | 5 | 6 |  |  |  | complexity is based on how much data originates out of M3 vs. AS400
Supplier (includes producers) | JDE | event | 5 | 6 |  |  |  | nature of integration is undefined

## Dailys Finance
Interface Description | Source | load frequency | complexity | duration | resources | Phase | Tech for load | comments
all CAT2 interfaces

## Dailys Manufacturing
Interface Description | Source | load frequency | complexity | duration | resources | Phase | Tech for load | comments

## Dailys COM
Interface Description | Source | load frequency | complexity | duration | resources | Phase | Tech for load | comments
should include TMS interfaces

## CAT2
Interface | Source | Description | load frequency | complexity | duration | resources | Phase | Tech for load | comments
Master Files:
Customer Master | M3 | Customer Master Import |  |  |  |  | Phase 1
Products (Items) | M3 | Product Master Import |  |  |  |  | Phase 1
BOM | M3 | Bill of Materials Master Import |  |  |  |  | Phase 1
Vendors (Suppliers) | M3 | Vendor Master Import |  |  |  |  | Phase 1
Material | CAT2? | Materials Master Import |  |  |  |  | Phase 1
Carrier | M3 | Carrier Master Import |  |  |  |  | Phase 1
Transaction Files:
Sales Orders | M3 | Sales Orders Import |  |  |  |  | Phase 1
Purchase Orders | M3 | Purchase Orders Import |  |  |  |  | Phase 1
Production (Mfg) Orders | M3 | Production (Manufacturing) Orders Import |  |  |  |  | Phase 1
Sales Orders (by line item) | CAT2 | Sales Order Export by Line Item |  |  |  |  | Phase 1
Sales Orders (by case) | CAT2 | Sales Orders Export by Cases |  |  |  |  | Phase 1
Sales Orders (by pallet) | CAT2 | Sales Orders Export by Pallets |  |  |  |  | Phase 1
Sales Order Status | CAT2 | Sales Order Status Update |  |  |  |  | Phase 1
Purchase Order Receipts | CAT2 | Purchase Orders Export |  |  |  |  | Phase 1
Physical Inventory Adj. | CAT2 | Physical Inventory Export |  |  |  |  | Phase 1
Issues/Returns | CAT2 | Issues/Returns Export |  |  |  |  | Phase 1
Case Details | CAT2 | Declaration of Production |  |  |  |  | Phase 1
Inventory Movements | CAT2 | Inventory Movement Transactions |  |  |  |  | Phase 1
Close Production Orders | CAT2 | Executed at end of day to close (complete) production orders |  |  |  |  | Phase 1